## Sheet1
Vendor | Data Integrity Report Status | Audit Status | In USA or OUS | Location | Services Audited | GxP Area | Audit Type | Audit Method | Proposed Quarter | VRTX QA Coordinator | CSQA Auditor | TW Report Number | Date of Intake | Date Q sent | Date Q Rcvd | Date On Site Scheduled | Audit Start Date | Audit End Date | Date Final Report Due | Date of audit pre-scope meeting | Date of audit debrief meeting | Date of Completion | Notes
CS Vendor 1 | (unknown) | Completed | OUS | Leeds, UK | Hosted artwork management system, | GIS | On Site | Qualification | Q1 | AlI Karaa | JA | 22401 | 2017-01-19 | (unknown) | (unknown) | 2017-01-30 | 2017-03-01 | 2017-03-02 | 2017-04-01 | (unknown) | 2017-03-02 | 2017-04-10
CS Vendor 2 | (unknown) | Completed | USA | Cincinnati, OH | Computerized Systems | GMP | On Site | Requalification | Q1 | WS | WS/ CL | 22586 | 2017-02-22 | (unknown) | (unknown) | 2017-02-22 | 2017-03-29 | 2017-03-30 | 2017-04-29 | (unknown) | 2017-04-07 | 2017-04-28
CS Vendor 3 | (unknown) | Completed | OUS | Wommelgem, Belgium |  | GIS | On Site | Requalification | Q1 | WS | WS | 22760 | 2017-02-22 | (unknown) | (unknown) | 2017-02-22 | 2017-03-07 | 2017-03-08 | 2017-04-07 | (unknown) | 2017-04-06 | 2017-04-07
CS Vendor 7 | (unknown) | Closed | USA | Princeton, NJ | Manged Service provider for system | GIS | On Site | Qualification | Q1 | AlI Karaa | MD | 23849 | 2017-03-08 | (unknown) | (unknown) | 2017-05-31 | 2017-07-25 | 2017-07-26 | 2017-08-25 | 2017-07-11 | 2017-08-01 | 2017-10-04
CS Vendor 9 | (unknown) | Completed | USA | Pleasanton, CA | DMS | GIS | On Site | Requalification | Q3 | Ali Karaa | AA | 23804 | 2017-04-03 | (unknown) | (unknown) | 2017-06-20 | 2017-08-22 | 2017-08-23 | 2017-09-22 | 2017-07-10 | 2017-08-28 | 2017-09-27
CS Vendor 10 | (unknown) | Completed | USA | Greenville, NC | Quality Systems Assessment; Software Development Life Cycle Process; Software Design, testing and implementation; change control and configuration management; 21CFR Part 11 capabilities; Problem reporting; Disaster recovery; Supporting SOPs and Test Evidence | GIS | On Site | Requalification | Q3 | Ali Karaa | AA | 23585 | 2017-04-03 | (unknown) | (unknown) | 2017-05-24 | 2017-07-18 | 2017-07-19 | 2017-08-18 | 2017-06-29 | 2017-07-24 | 2017-08-18
CS Vendor 15 | (unknown) | Completed | OUS | Richmond, BC Canada | GMP Temperature and Humidity Monitoring System | GIS | On Site | Requalification | Q3 | Ali Karaa | CL | 23812 | 2017-04-03 | (unknown) | (unknown) | 2017-06-15 | 2017-08-14 | 2017-08-15 | 2017-09-14 | 2017-07-25 | 2017-08-22 | 2017-09-27
CS Vendor 17 | (unknown) | Completed | USA | Princeton, NJ | Quality Systems Assessment; System Life Cycle Process; Software Design and Testing; Change Control; User Acceptance Process; Part 11 Assesment; Security, Network and Disatser Recovery Controls; A selection of related SOPs and validation documentation (filed in ) | GIS | On Site | Requalification | Q3 | Ali Karaa | MD | 23536 | 2017-04-03 | (unknown) | (unknown) | 2017-05-26 | 2017-07-13 | 2017-07-13 | 2017-08-12 | 2017-06-30 | 2017-07-18 | 2017-08-11
CS Vendor 18 | (unknown) | Closed | USA | Cary, NC | SDLC ( Software Development Life Cycle) and SLC (System Life Cycle) processes. | GIS | Questionnaire | Requalification | Q3 | Ali Karaa | MD | 23535 | 2017-04-03 | 2017-06-16 | 2017-06-30 | (unknown) | (unknown) | (unknown) | 2017-07-30 | (unknown) | (unknown) | 2017-08-10
CS Vendor 19 | (unknown) | Closed | USA | Burlington, MA | Tape Vaulting Services | GIS | On Site | Requalification | Q3 | Ali Karaa | BM | 23426 | 2017-04-03 | (unknown) | (unknown) | 2017-05-24 | 2017-07-11 | 2017-07-11 | 2017-08-10 | 2017-06-27 | 2017-07-14 | 2017-08-10
CS Vendor 21 | (unknown) | Completed | USA | Palo Alto, CA | Software Service Provider | GIS | Questionnaire | Requalification | Q3 | AlI Karaa | CL | 23995 | 2017-07-11 | 2017-08-07 | 2017-08-29 | (unknown) | (unknown) | (unknown) | 2017-09-28 | (unknown) | (unknown) | 2017-09-28
CS Vendor 23 | (unknown) | Completed | USA | Boston, MA | Data Review Process | GCP | On Site | Internal | Q2 | AlI Karaa | JR | [10 empty] | 2017-07-13